## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43209 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One: Group Formation | 2018-04-19 | 2018-04-27 | 8 | 8 | 0 | 100%
Task Two: Problem Selection | 2018-04-27 | 2018-05-05 | 8 | 8 | 0 | 100%
Task Three: Literature Review | 2018-05-05 | 2018-05-10 | 5 | 1.25 | 3.75 | 25%
Task Four: Data Wrangling | 2018-05-10 | 2018-05-14 | 4 | 0 | 4 | 0%
Task Five: Modelling | 2018-05-14 | 2018-05-16 | 2 | 0 | 2 | 0%
Task Six: Analysis | 2018-05-16 | 2018-05-17 | 1 | 0 | 1 | 0%
Task Seven: Insight | 2018-05-17 | 2018-05-18 | 1 | 0 | 1 | 0%
Task Eight: Final Report | 2018-05-18 | 2018-05-19 | 1 | 0 | 1 | 0%
Task Nine: Group presentation | 2018-05-19 | 2018-05-22 | 3 | 0 | 3 | 0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.